## Summary
美博工程服務有限公司
MS_Q1241_24_kp (MTR C9644-24C Extension of Fitness Room at KBD Recreation & Sports Centre)
(Project No. MS_Q1241_24)
地盤糧期狀況
工期 | 12/2024 - 01/2026 | (390天)
總承建商(MC): | Mepork Engineering Service Limited
承包商(SUB-CON):
承包商(SUB-CON):
承建金額: | 7400000
(a) |  | Option 1
(b) |  | Option 2
(c)
(d)
(A) Sub-total: | 7400000
承包商(SUB-CON): | 宏發工程公司
(a) | 1900000 | Builder's Works | 宏發建築工程公司 | SC-003
(b) | 800000 | FS | 大同工程有限公司 | SC-002
(c) | 1212880 | EL Labour | 照明工程有限公司 | SC-010 & SC-010.1
(d) | 800000 | ECS | 盈泊工程公司 | SC-004
(e) | 15500 | Design of Hoarding, SE | 華文工程有限公司 | SC-008 & SC-008.1
(f)
(B) Sub-total: | 4728380
(C) = (A) - (B) 利潤: | 2671620
Less Expenses : | 44360 | Insurance - EC | 恒傑保險業務有限公司 | O-001
Less Expenses : | 15000 | Q167/21 搭架比EMSD驗收燈柱 | 宏發建築工程公司 | SC-003A
Less Expenses : | 83000 | 代買冷氣機 | 盈泊工程公司 | SC-004A
Less Expenses : | 27242.5 | Levies | 環境保護署 | O-005
Less Expenses : | 284000 | Safety | 滅火筒安全顧問 | O-006 & O-006.1
Less Expenses : | 2000 | CP Training | MTR | O-007
Less Expenses : | 14006 | Levies | 建造業議會 | O-012
Less Expenses : | 12038.9 | Miscellaneous |  | O-013
Less Expenses : | 6279 | Levies | 肺塵埃沉着病補償基金委員會 | O-014
Less Expenses : | 1640 | Body Check | 聯康醫療 | O-009
Less Expenses : | 174600 | Light fitting | ALCO LIGHTING (H.K.) LTD | M-015
Less Expenses : | 187121.1 | EL - Material | 信成電器材料有限公司 | M-011.1 - M-011.19
Less Expenses :
Less Expenses :
Less Expenses :
Less Expenses :
Less Expenses :
Less Expenses : |  |  |  | Remark:
(D) Total Sum of Profit (TBC): | 1820332.5 |  |  | 12000 | 扣宏發
|  |  |  | 1500 | CP 扣判頭
(E) 預計利潤: | 784400 | (10.6% Profit)
(F) = (E) - (D) 其他項目支出: | 1035932.5
Mepork Engineering Services Limited | [6 empty] | 承包商(SUB-CON)
糧款期數 | 申請糧款日期 | 申請工程金額 HK$ | 申請工程金額 百分比 | 收入 （則師批款) HK$ | 則師批款 百分比 | 則師批數日期 | 支出 （美博批款) HK$ | 則師批款 百分比 | 美博批數日期
Interim Payment No. | Applied Date | Payment Application | % | Payment Certified Amount | % | Payment Certificate Date | Payment Certified Amount | % | Payment Certificate Date
IP-01 | 2025-02-15 | 286605 | 3.873% | 182481.3 | 2.466% | 2025-03-10 |  | 0%
IP-02 | 2025-03-17 | 177763.05 | 6.275% | 99373.5 | 3.809% | 2025-04-09 |  | 0%
IP-03 | 2025-05-06 | 278784.23 | 10.04% | 249814.8 | 7.185% | 2025-05-29 |  | 0%
IP-04 | 2025-05-09 | 268119.45 | 13.67% | 178865.1 | 9.602% | 2025-07-04 |  | 0%
IP-05 | 2025-07-21 | 848025.45 | 25.13% | 557768.7 | 17.14% | 2025-08-12 |  | 0%
IP-06 | 2025-08-20 | 841890.15 | 36.5% | 350842.5 | 21.88% | 2025-09-11 |  | 0%
IP-07 | 2025-09-23 | 987280.43 | 49.84% | 431916.3 | 27.72% | 2025-10-16 |  | 0%
IP-08 | 2025-10-22 | 1190913.53 | 65.94% | 591593.4 | 35.71% | 2025-11-18 |  | 0%
IP-09 | 2025-12-09 | 2139244.9 | 94.85% | 1543503.4 | 56.57% | 2026-01-01 |  | 0%
IP-10 | 2026-01-06 | 1434253.25 | 114.2% | 562026 | 64.16% | 2026-01-28 |  | 0%
|  |  |  | 4748185 |  |  | 0
|  |  | 總收入: | 4748185 |  |  | 4748185
Prepared By: | Katie Puk |  | 總支出: | -5395140.25
Updated on: | 2026-06-05 14:30 |  | 墊支: | -646955.25

## 代支工程, 物料
MS_Q1241_24_kp (MTR C9644-24C Extension of Fitness Room at KBD Recreation & Sports Centre)
代支工程總表
Updated on 12/12/2024
No. | Link | Invoice Date | Invoice No. | Quotation No. | Sub-contractors' No | Company Name | Company Name (in Chinese) | Description | Contract Amount (HK$) | Paid Amount (HK$) | Remainder Amount (HK$) | OA日期 | OA編號 | MC IP-No. | B/C to sub-contractor | Sub-IP No. | Reamrk
1 | 1 | 2024-12-11 | I0482530 |  | O-001 | REALIFE INSURANCE BROKERS LTD. | 恒傑保險業務有限公司 | Insurance - EC | 44360 | 44360 | 0 | [5 empty] | Pokfulam No. 599 Transfer to WCH No.1 | =HYPERLINK("Q:\Project No. 016A - HKSR PHI Renovation at Pokfulam\P1 - Payment\Payment Records\"&A5&".PDF",A5)
2 | 2 | 2024-12-19 | Q-CEL-FS-2411-01 |  | SC-002 | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Fire Services Installation | 800000 | 100000 | 700000
3 | 3 | 2024-12-20 |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 200000 | 1700000
4 | 4 | 2024-12-16 | 12024180 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-01 | 800000 | 150000 | 650000
5 | 5 | 2024-12-31 | 705330010 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 15000 | 12242.5
6 | 6 | 2025-01-02 | INV2/1/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 7742 | 264258
7 | 7 | 25/1/2025 |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 180000 | 1720000
8 | 8 | 2025-02-02 | 102-004363-001 |  | O-007 | MTR | 0 | CP Training | 2000 | 500 | 1500
9 | 9 | 2025-02-13 | INV13/2/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
10 | 10 | 2025-02-28 |  |  | O-007 | MTR | 0 | CP Training | 2000 | 1000 | 1000
11 | 11 | 2025-03-10 | INV10/3/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
12 | 12 | 2025-03-19 | DN18553-QL |  | O-009 | UCMG | 聯康醫療 | Body Check | 1640 | 540 | 1100
13 | 13 | 2025-04-01 | INV 1/4/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
14 | 14 | 2025-04-16 | DN18593-QL |  | O-009 | UCMG | 聯康醫療 | Body Check | 1640 | 270 | 1370
15 | 15 | 2025-04-02 | INV 2/4/2025 |  | O-006.1 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety Review | 12000 | 12000 | 0
16 | 16 | 2025-05-08 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-01 | 1100000 | 126628 | 973372
17 | 17 | 2025-03-04 | MB-202402b |  | SC-008 | WAH MAN ENGINEERING COMPANY | 華文工程有限公司 | Design of Hoarding | 9500 | 9500 | 0
18 | 18 | 2025-05-15 | INV 15/5/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
19 | 19 | 2025-05-14 |  |  | O-007 | MTR | 0 | CP Training | 2000 | 500 | 1500
20 | 20 | 2025-06-10 | DN3347788 |  | O-012 | CONSTRUCTION INDUSTRY COUNCIL | 建造業議會 | Levies | 14006 | 1493 | 12513
21 | 21 | 2025-06-27 |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 190000 | 1710000
22 | 22 | 2025-06-27 |  |  | SC-002 | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Fire Services Installation | 800000 | 235000 | 565000
23 | 23 | 2025-06-13 | INV3//2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
24 | 24 | 2025-06-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-02 | 1100000 | 108500 | 991500
25 | 25 |  |  |  | O-013 | Miscellaneous | 0 | 0 | 12038.9 | 1920 | 10118.9
26 | 26 | 2025-06-24 | DN3581600 |  | O-014 | PNEUMOCONIOSIS COMPENSATION FUND BOARD | 肺塵埃沉着病補償基金委員會 | Levies | 6279 | 422 | 5857
27 | 27 | 2025-06-17 | DN18711-QL |  | O-009 | UCMG | 聯康醫療 | Body Check | 1640 | 280 | 1360
28 | 28 | 2025-04-10 | 64440 |  | M-011.1 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 32940 | 32940 | 0
29 | 29 | 2025-04-06 | 64331 |  | M-011.2 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 39055 | 39055 | 0
30 | 30 | 2025-04-05 | 64187 |  | M-011.3 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 21960 | 21960 | 0
31 | 31 | 2025-04-28 | 64286 |  | M-011.4 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 19740 | 19740 | 0
32 | 32 | 2025-04-26 | 64272 |  | M-011.5 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 2080 | 2080 | 0
33 | 33 | 2025-07-14 | INV14/7/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
34 | 34 | 2025-07-17 | 12025082 |  | SC-004A | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-02 (VO) | 83000 | 83000 | 0
35 | 35 | 2025-06-18 | IVA01106-25 |  | M-015 | ALCO LIGHTING (H.K.) LTD | 0 | Light fitting | 174600 | 174600 | 0
36 | 36 | 2025-07-16 | 12025064 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-03 | 800000 | 138000 | 662000
37 | 37 | 2025-07-24 | 705330028 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 4562.5 | 22680
38 | 38 | 2025-06-10 | 64555 |  | M-011.6 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 5400 | 5400 | 0
39 | 39 | 2025-05-21 | 64426 |  | M-011.8 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 1988.3 | 1988.3 | 0
40 | 40 | 2025-05-21 | 64425 |  | M-011.7 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 1353 | 1353 | 0
41 | 41 |  |  |  | SC-008.1 | WAH MAN ENGINEERING COMPANY | 華文工程有限公司 | Structural Engineering Consultancy | 6000 | 6000 | 0
42 | 42 | 2025-07-29 | DN2507000481 |  | O-009 | UCMG | 聯康醫療 | Body Check | 1640 | 270 | 1370 |  |  |  | 扣宏發
43 | 43 | 2025-08-05 | Q-CEL-FS-2411-01 |  | SC-002 | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Fire Services Installation | 800000 | 116250 | 683750
44 | 44 | 2025-07-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-03 | 1100000 | 54597.3 | 1045402.7
45 | 45 |  |  |  | O-013 | Miscellaneous | 0 | 0 | 12038.9 | 6146.9 | 5892
46 | 46 | 2025-07-29 | DN2507000479 |  | O-009 | UCMG | 聯康醫療 | Body Check | 1640 | 280 | 1360 |  |  |  | 扣盈泊
47 | 47 | 2025-08-19 | INV-WF-20250519 |  | SC-003A | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Q167/21 搭架比EMSD驗收燈柱 | 15000 | 15000 | 0
48 | 48 | 2025-08-13 | 12025088 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-04 | 800000 | 108000 | 692000
49 | 49 | 2025-06-09 | 3022374 |  | O-013 | Miscellaneous | 0 | 0 | 12038.9 | 460 | 11578.9
50 | 50 | 2025-08-13 | INV13/8/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
50A | 50A | 2025-07-15 | 250713 |  | O-017 | Firewood Engineering Ltd. | 積富工程有限公司 | CP(NT)/Fire Marshal | 1500 | 1500 | 0 |  |  |  | 扣宏發
51 | 51 | 2025-09-02 | 12025105 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-05 | 800000 | 80000 | 612000
52 | 52 | 9/9/205 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-04 | 1100000 | 158545.5 | 941454.5
53 | 53 | 2025-07-18 | 64769 |  | M-011.15 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 8909 | 8909 | 0
54 | 54 | 2025-07-18 | 64768 |  | M-011.14 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 6410 | 6410 | 0
55 | 55 | 2025-09-03 | 705330028 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 540 | 26702.5
56 | 56 | 2025-08-01 | 64864 |  | M-011.10 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 15497.2 | 15497.2 | -1.819e-12
57 | 57 | 2025-07-30 | 64846 |  | M-011.13 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 900 | 900 | 0
58 | 58 | 2025-08-04 | 64884 |  | M-011.12 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 6120 | 6120 | 0
59 | 59 | 2025-07-18 | 64767 |  | M-011.11 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 7200 | 7200 | 0
60 | 60 | 2025-07-25 | 64827 |  | M-011.9 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 2393.6 | 2393.6 | 0
61 | 61 | 2025-09-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-05 | 1100000 | 157554.65 | 942445.35
62 | 62 | 2025-09-16 | INV16/9/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
63 | 63 | 2025-09-29 | DN3400538 |  | O-012 | CONSTRUCTION INDUSTRY COUNCIL | 建造業議會 | Levies | 14006 | 5229 | 8777
64 | 64 | 2025-10-06 | DN3648839 |  | O-014 | PNEUMOCONIOSIS COMPENSATION FUND BOARD | 肺塵埃沉着病補償基金委員會 | Levies | 6279 | 1480 | 4799
65 | 65 |  |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 199500 | 1700500
66 | 66 | 2025-10-15 | 705330028 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 500 | 26742.5
67 | 67 | 2025-10-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-06 | 1100000 | 56468 | 1043532
68 | 68 | 2025-10-20 | INV20/10/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
69 | 69 | 2025-10-09 | 12025121 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-06 | 800000 | 80000 | 720000
70 | 70 | 2025-11-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-07 | 1100000 | 14250 | 1085750
71 | 71 | 2025-11-06 | 12025132 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-07 | 800000 | 80000 | 720000
72 | 72 | 2025-09-25 | 65240 |  | M-011.19 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 4363 | 4363 | 0
73 | 73 | 2025-09-09 | 65083 |  | M-011.17 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 1803 | 1803 | 0
74 | 74 | 2025-11-18 | 65077 |  | M-011.16 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 2584 | 2584 | 0
75 | 75 | 2025-09-10 | 65088 |  | M-011.18 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 6425 | 6425 | 0
76 | 76 | 2025-11-18 | INV18/11/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
77 | 77 | 2025-12-04 |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 365750 | 1534250
78 | 78 | 2025-11-29 | 12025137 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation - IP-08 | 800000 | 100000 | 700000
79 | 79 | 2025-11-06 | Q-CEL-FS-2411-01-VO-01-R1 |  | SC-002A | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Supply Smoke Detector | 12000 | 12000 | 0 | [5 empty] | 扣宏發
80 | 80 | 2025-12-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-08 | 1100000 | 68537.75 | 1031462.25
81 | 81 | 2025-12-12 |  |  | O-013 | Miscellaneous | 0 | 0 | 12038.9 | 1827 | 10211.9
82 | 82 | 2025-12-19 |  |  | O-013 | Miscellaneous | 0 | 0 | 12038.9 | 1685 | 10353.9
83 | 83 | 2025-12-26 | INV26/12/2025 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
84 | 84 | 2025-12-01 | P24-28 |  | SC-010.1 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-09(VO-01 (EI-01)) | 112880 | 56440 | 56440
85.1 | 85.1 | 2026-02-01 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-11 | 1100000 | 45698.8 | 1054301.2
85 | 85 | 2026-02-01 | P24-28 |  | SC-002 | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Fire Services Installation | 800000 | 118750 | 681250
86 | 86 | 2026-01-20 | DN3717931 |  | O-014 | PNEUMOCONIOSIS COMPENSATION FUND BOARD | 肺塵埃沉着病補償基金委員會 | Levies | 6279 | 1174 | 5105
87 | 87 | 2026-01-27 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-10 | 1100000 | 38000 | 1062000
88 | 88 | 2025-11-03 | 65300 |  | M-011.20 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 475.4 | 475.4 | 0
89 | 89 | 2026-03-05 | 65758 |  | M-011.22 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 275.2 | 275.2 | 0
90 | 90 | 2026-01-10 | 65581 |  | M-011.25 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 8460 | 8460 | 0
91 | 91 | 2026-01-19 | 65617 |  | M-011.24 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 1625 | 1625 | 0
91.1 | 91.1 | 2026-01-10 | 65579 |  | M-011.23 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 6335 | 6335 | 0
91.2 | 91.2 | 4/32/2026 | 65750 |  | M-011.21 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material | 16028.8 | 16028.8 | 0
92 | 92 | 2026-02-06 | 705330028 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 2940 | 24302.5
93 | 93 | 2026-01-22 | I0521885 |  | O-001.1 | REALIFE INSURANCE BROKERS LTD. | 恒傑保險業務有限公司 | Insurance - EC Extension | 12366.35 | 12366.35 | 0
94 | 94 | 2026-02-23 | INV05/2/2026 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
95 | 95 | 2026-03-03 | 705330028 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 3180 | 24062.5
96 | 96 | 2026-03-09 |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 270750 | 1629250
97 | 97 | 2026-03-11 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-12 | 1100000 | 103288.75 | 996711.25
98 | 98 | 2026-03-09 | INV9/3/2026 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
99 | 99 | 2026-03-10 | INV10/3/2026 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
100 | 100 | 2026-03-24 | DN3760238 |  | O-014 | PNEUMOCONIOSIS COMPENSATION FUND BOARD | 肺塵埃沉着病補償基金委員會 | Levies | 6279 | 3203 | 3076
101 | 101 | 2026-03-13 | 12025160 |  | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation | 800000 | 20000 | 780000
102 | 102 | 2026-04-08 | DN3480340 |  | O-012 | CONSTRUCTION INDUSTRY COUNCIL | 建造業議會 | Levies | 14006 | 7284 | 6722
103 | 103 | 2026-04-13 | P24-28 |  | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-13 | 1100000 | 107801.25 | 992198.75
104 | 104 |  |  |  | SC-003B | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Tony 帳款 | 647200 | 350700 | 296500
105 | 105 | 2026-04-01 | P24-28 |  | M-015.1 | ALCO LIGHTING (H.K.) LTD | 0 | Light fitting | 32220 | 32220 | 0
106 | 106 | 2026-04-27 | P24-28 |  | SC-010.1 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - IP-14(VO-01 (EI-01)) | 112880 | 11288 | 101592
107 | 107 | 2026-05-18 |  |  | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works | 1900000 | 270750 | 1629250
108 | 108 | 2026-04-29 | 705330028 |  | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal | 27242.5 | 520 | 26722.5
109 | 109 | 2026-05-05 | INV5/5/2026 |  | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety | 272000 | 16000 | 256000
110 | 110 | 2026-04-08 | BLSA260430 |  | SC-020 | Brilliant Lighting Limited | 恒亮照明有限公司 | LED Exit Sign,由Dennis Chan 代付 | 277 | 277 | 0
111 | 111
112 | 112
113 | 113
114 | 114
115 | 115
116 | 116
117 | 117
118 | 118
119 | 119
120 | 120
121 | 121
122 | 122
123 | 123
124 | 124
125 | 125
126 | 126
127 | 127
128 | 128
129 | 129
130 | 130
131 | 131
132 | 132
133 | 133
134 | 134
135 | 135
136 | 136
137 | 137
138 | 138
139 | 139
140 | 140
141 | 141
142 | 142
143 | 143
[9 empty] | 42280329.85 | 5395140.25
|  | Sub-IP No. | 14650000 | [6 empty] | MC IP-No. |  | Mepork (MC)
|  | 1 | 0 | 14650000 | [5 empty] | 1 |  | 0
|  | 2 | 0 | 14650000 | [5 empty] | 2 |  | 0
|  | 3 | 0 | 14650000 | [5 empty] | 3 |  | 0
|  | 4 | 0 | 14650000 | [5 empty] | 4 |  | 0
|  | 5 | 0 | 14650000 | [5 empty] | 5 |  | 0
|  | 6 | 0 | 14650000 | [5 empty] | 6 |  | 0
|  | 7 | 0 | 14650000 | [5 empty] | 7 |  | 0
|  | 8 | 0 | [6 empty] | 8 |  | 0
|  | 9 | 0 | [6 empty] | 9 |  | 0
|  | 10 | 0 | [6 empty] | 10 |  | 0 | Total Amount | TBC
|  |  | 0 | 14650000 | [7 empty] | 0 | 14650000 | 0

## Project Summary
美博工程服務有限公司
MS_Q1241_24_kp (MTR C9644-24C Extension of Fitness Room at KBD Recreation & Sports Centre)
總承建商(MC): | Mepork Engineering Services Limited | [6 empty] | 承建金額: | 7400000
[8 empty] | (a) |  |  | $1,720,000.00 Contingency
[8 empty] | (A) Sub-total: | 7400000
Item | Sub-contractors' No. | Quotation Copy | Sub-contractors' Name | Company Name (in Chinese) | Nature of S/C Works | Contract Charge | Contract Sum | VO | Revised Contract Sum | Remark | 合約會簽表 (10萬以上) | Contract | 定標會議紀錄 (100萬以上) | 報價已簽名 | 正本已存檔 | OA
1 | O-001 | O-001 | REALIFE INSURANCE BROKERS LTD. | 恒傑保險業務有限公司 | Insurance - EC |  | 44360 |  | 44360 |  | - | OK | OK |  | OK | 2024-12-14 | 0.5995%
1A | O-001.1 | O-001.1 | REALIFE INSURANCE BROKERS LTD. | 恒傑保險業務有限公司 | Insurance - EC Extension |  | 12366.35 |  | 12366.35 | [6 empty] | 2026-01-27
2 | SC-002 | SC-002 | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Fire Services Installation |  | 800000 |  | 800000 |  | OK | OK | - | OK | Quotation saved | 2024-12-21
2A | SC-002A | SC-002A | CHASE ENGINEERING LIMITED | 大同工程有限公司 | Supply Smoke Detector |  | 12000 |  | 12000 | 扣宏發 | [5 empty] | 2025-11-17
3 | SC-003 | SC-003 | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Builder's Works |  | 1900000 |  | 1900000 |  | OK | OK |  | OK | Quotation saved | 2024-12-21
3A | SC-003A | SC-003A | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Q167/21 搭架比EMSD驗收燈柱 |  | 15000 |  | 15000 | [6 empty] | 2025-06-20
3B | SC-003B |  | WANG FAT CONSTRUCTION CO. | 宏發建築工程公司 | Tony 帳款 |  | 647200 |  | 647200
4 | SC-004 | SC-004 | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | MVAC Installation |  | 800000 |  | 800000 |  | OK | OK | - | OK | Quotation saved | 2024-12-21
5A | SC-004A | SC-004A | YING PAK ENGINEERING COMPANY | 盈泊工程公司 | 代買冷氣機 |  | 83000 |  | 83000 | [6 empty] | 2025-07-23
5 | O-005 | O-005 | Environmental Protection Department | 環境保護署 | Waste Dispoal |  | 27242.5 |  | 27242.5 | $15,000 Deposit | - | - | - | - | - | -
6 | O-006 | O-006 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety |  | 272000 |  | 272000 | $16,000 / month | OK | - | - | OK | OK | 2024-12-20
6.2 | O-006.2 | O-006.2 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety 延期 |  | 112000 |  | 112000 | [6 empty] | 2026-06-02
6.1 | O-006.1 | O-006.1 | FIRE EXTINGUISHER SAFETY CONSULTANT | 滅火筒安全顧問 | Safety Review |  | 12000 |  | 12000 |  | - | - | - | OK | OK | 2025-04-28
7 | O-007 | O-007 | MTR |  | CP Training |  | 2000 |  | 2000 |  | - | - | - | - | - | -
8 | SC-008 | SC-008 | WAH MAN ENGINEERING COMPANY | 華文工程有限公司 | Design of Hoarding |  | 9500 |  | 9500
8.1 | SC-008.1 | SC-008.1 | WAH MAN ENGINEERING COMPANY | 華文工程有限公司 | Structural Engineering Consultancy |  | 6000 |  | 6000 | [6 empty] | 2025-08-04
9 | O-009 | O-009 | UCMG | 聯康醫療 | Body Check |  | 1640 |  | 1640
10 | SC-010 | SC-010 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL |  | 1100000 |  | 1100000
10.1 | SC-010.1 | SC-010.1 | CHIU MING COMPANY LIMITED | 照明工程有限公司 | EL - VO-01 (EI-01) |  | 112880 |  | 112880 | [6 empty] | 2025-01-12
11 | M-011.1 | M-011.1 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 32940 |  | 32940 | [6 empty] | 2025-07-23
11 | M-011.2 | M-011.2 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 39055 |  | 39055 | [6 empty] | 2025-07-23
11 | M-011.3 | M-011.3 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 21960 |  | 21960 | [6 empty] | 2025-07-23
11 | M-011.4 | M-011.4 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 19740 |  | 19740 | [6 empty] | 2025-07-23
11 | M-011.5 | M-011.5 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 2080 |  | 2080 | [6 empty] | 2025-07-23
11 | M-011.6 | M-011.6 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 5400 |  | 5400 | [6 empty] | 2025-07-23
11 | M-011.7 | M-011.7 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 1353 |  | 1353 | [6 empty] | 2025-07-23
11 | M-011.8 | M-011.8 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 1988.3 |  | 1988.3 | [6 empty] | 2025-07-23
11 | M-011.9 | M-011.9 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 2393.6 |  | 2393.6 | [6 empty] | 2025-07-23
11 | M-011.10 | M-011.10 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 15497.2 |  | 15497.2 | [6 empty] | 2025-07-23
11 | M-011.11 | M-011.11 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 7200 |  | 7200 | [6 empty] | 2025-07-23
11 | M-011.12 | M-011.12 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 6120 |  | 6120 | [6 empty] | 2025-07-23
11 | M-011.13 | M-011.13 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 900 |  | 900 | [6 empty] | 2025-07-23
11 | M-011.14 | M-011.14 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 6410 |  | 6410 | [6 empty] | 2025-07-23
11 | M-011.15 | M-011.15 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 8909 |  | 8909 | [6 empty] | 2025-07-23
11 | M-011.16 | M-011.16 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 2584 |  | 2584 | [6 empty] | 2025-07-23
11 | M-011.17 | M-011.17 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 1803 |  | 1803 | [6 empty] | 2025-07-23
11 | M-011.18 | M-011.18 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 6425 |  | 6425 | [6 empty] | 2025-07-23
11 | M-011.19 | M-011.19 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 4363 |  | 4363 | [6 empty] | 2025-07-23
11 | M-011.20 | M-011.20 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 475.4 |  | 475.4 | [6 empty] | 2026-04-30
11 | M-011.21 | M-011.21 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 16028.8 |  | 16028.8 | [6 empty] | 2026-04-30
11 | M-011.22 | M-011.22 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 275.2 |  | 275.2 | [6 empty] | 2026-04-30
11 | M-011.23 | M-011.23 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 6335 |  | 6335 | [6 empty] | 2026-04-30
11 | M-011.24 | M-011.24 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 1625 |  | 1625 | [6 empty] | 2026-04-30
11 | M-011.25 | M-011.25 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 8460 |  | 8460 | [6 empty] | 2026-04-30
11 | M-011.26 | M-011.26 | SHUN SHING ELECTRICALS CO. LTD | 信成電器材料有限公司 | EL - Material |  | 7832 |  | 7832 | [6 empty] | 2026-06-01
11 | M-011.27 | M-011.27 | [6 empty] | 0
11 | M-011.28 | M-011.28 | [6 empty] | 0
11 | M-011.29 | M-011.29 | [6 empty] | 0
11 | M-011.30 | M-011.30 | [6 empty] | 0
11 | M-011.31 | M-011.31 | [6 empty] | 0
12 | O-012 | O-012 | CONSTRUCTION INDUSTRY COUNCIL | 建造業議會 | Levies |  | 14006 |  | 14006
13 | O-013 | O-013 | Miscellaneous |  |  |  | 12038.9 |  | 12038.9
14 | O-014 | O-014 | PNEUMOCONIOSIS COMPENSATION FUND BOARD | 肺塵埃沉着病補償基金委員會 | Levies |  | 6279 |  | 6279
15 | M-015 | M-015 | ALCO LIGHTING (H.K.) LTD |  | Light fitting |  | 174600 |  | 174600 | [6 empty] | 2025-07-23
15 | M-015.1 | M-015.1 | ALCO LIGHTING (H.K.) LTD |  | Light fitting |  | 32220 |  | 32220 | [6 empty] | 2026-04-15
16 | O-016 | O-016 | UCEM | 聯康醫療 |  |  |  |  | 0
17 | O-017 | O-017 | Firewood Engineering Ltd. | 積富工程有限公司 | CP(NT)/Fire Marshal | * | 1500 |  | 1500 | $1,500/CP(NT) $1,450/Fire Marshal 扣判頭 | [5 empty] | 2025-08-11
18 | O-018 | O-018 | South China Inspection & Testing Ltd. | 華南檢測有限公司 | Testing |  | 3280 |  | 3280 | [6 empty] | 2026-06-01
18.1 | O-018.1 |  | South China Inspection & Testing Ltd. | 華南檢測有限公司 | 由宏發建築工程公司代付 |  | 43640 |  | 43640 | [6 empty] | 2026-06-04
19 | SC-019 | SC-019 | CHING YAN ENGINEERING COMPANY LIMITED | 晴昕工程有限公司 | 復康會 No. 752 To Q1241 |  | 95000 |  | 95000 | [6 empty] | 2026-06-05
20 | SC-020 | SC-020 | Brilliant Lighting Limited | 恒亮照明有限公司 | LED Exit Sign,由Dennis Chan 代付 |  | 277 |  | 277 | [6 empty] | 2026-06-05
21 | SC-021 | SC-021 | [6 empty] | 0
22 | SC-022 | SC-022 | [6 empty] | 0
23 | SC-023 | SC-023 | [6 empty] | 0
[8 empty] | (B) Sub-total : | 6580182.25
[8 empty] | (C)Excluded Contract Charge item : | -1500 | *
| M-0XX | Material | [5 empty] | 財務會作調撥(人工分攤) | 1362556.4
| SC-0XX | Sub-Contractor | [5 empty] | (D) = (B)+(C): | 7941238.65
| O-0XX | Other | [5 empty] | (E) = (A)-(D)預計利潤: | -541238.65 | (原預計利潤率6.7%)
[8 empty] | 預計利潤率: | -7.314%