## Summary
美博工程服務有限公司
MS_Q1161_25_jc (MTR - K2297.C-25C Replacement of Platform Awnings at EAL Stations (Stage 3)
(Project No. MS_Q1161_25) |  |  |  |  | LOA | 2025-11-07
地盤糧期狀況 |  |  |  |  | 起期 | 2025-11-14 | 2026-10-15
[5 empty] | 工期(日) | 990 | 655
總承建商(MC): | Mepork Engineering Service Limited |  |  |  | 預計完工 | 2028-07-31 | 33.84%
承建金額: | 51600000
(a)
(b)
(c)
(d)
(A) Sub-total: | 51600000
承包商(SUB-CON):
(a) | 40580000 | 煒浩工程有限公司 | Whole works | SC-001
(b)
(c)
(d)
(e)
(B) Sub-total: | 40580000
[7 empty] | MTR Cert | 3494780.1 | 6.773%
(C) = (A) - (B) 利潤: | 11020000 | [5 empty] | Remain | 48105219.9 | 93.23%
Less Expenses : | -515019.6 | 保險有限公司 | Insurance
Less Expenses : |  | 安全主任 | RSO |  |  |  | SubCon | 2360000 | 5.816%
Less Expenses : | [6 empty] | Remain | 38220000 | 94.18%
Less Expenses :
(D) Total Sum of Profit (TBC): | 10504980.4
(E) 預計利潤: | 3612000 | (7.0% Profit)
(F) = (E) - (D) 其他項目支出: | 6892980.4
[7 empty] | 煒浩 | 則師批款 百分比 | 美博批數日期
Mepork Engineering Services Limited | [6 empty] | SC-001
糧款期數 | 申請糧款日期 | 申請工程金額 HK$ | 申請工程金額 百分比 | 收入 （則師批款) HK$ | 則師批款 百分比 | 則師批數日期 | 支出 （美博批款) HK$
Interim Payment No. | Applied Date | Payment Application | % | Payment Certified Amount | % | Payment Certificate Date | Payment Certified Amount | % | Payment Certificate Date
IP-01 | 2026-01-06 | 1536029.1 | 2.977% | 1090362.6 | 2.113% | 2026-02-06 | 1250000 | 3.08% | 2026-01-07
IP-02 | 2026-02-05 | 2862915.61 | 8.525% | 2404417.5 | 6.773% | 2026-03-13 | 1110000 | 5.816% | 2026-02-09
IP-03 | 2026-03-18 | 1330362.49 | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-04 |  |  | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-05 |  |  | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-06 |  |  | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-07 |  |  | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-08 |  |  | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-09 |  |  | 11.1% |  | 6.773% |  | 0 | 5.816%
IP-10 |  |  | 11.1% |  | 6.773% |  |  | 5.816%
|  |  |  | 3494780.1 |  |  | 2360000
|  |  | 總收入: | 3494780.1
Prepared By: | Joseph Chung |  | 總支出: | -17612553.6
Updated on: | 2026-10-15 10:49 |  | 墊支: | -14117773.5

## 代支工程 物料
MS_Q1161_25_jc (MTR - K2297.C-25C Replacement of Platform Awnings at EAL Stations (Stage 3)
代支工程總表
No. | Link | Invoice Date | Invoice No. | Quotation No. | Sub-contractors' No | Company Name | Company Name (in Chinese) | Description | Contract Amount (HK$) | Paid Amount (HK$) | Remainder Amount (HK$) | OA日期 | OA編號 | MC IP-No. | B/C to sub-contractor | Sub-IP No. | Reamrk
1 | 1 | 2026-01-06 | 10-2506-INV-001 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 01 | 40580000 | 1250000 | 39330000 |  |  |  |  | IP-01
2 | 2 | 2025-11-21 | G208929D |  | O-002 | Storfield Insurance Consultants Ltd | 多福保險顧問有限公司 | Insurance | 515019.6 | 515019.6 | 0
3 | 3 | 2026-02-04 | 10-2506-INV-002(R1) |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 02 | 40580000 | 1110000 | 38220000 |  |  |  |  | IP-02
4 | 4 | 2026-03-09 | 10-2506-INV-003 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 03 | 40580000 | 995000 | 37225000
5 | 5 | 2026-03-17 | INV-2026-013 |  | SC-004 | MS Engineering HK Limited | 文生工程有限公司 | 中土Project | 2500000 | 1000000 | 1500000
6 | 6 | 2026-03-31 | MCEL TKL 20260331 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 11000 | 253000
7 | 7 | 2026-04-09 | 10-2506-INV-004-R1 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 04 | 40580000 | 1102000 | 36123000
8 | 8 | 2026-05-08 | 10-2506-INV-005 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 05 | 40580000 | 1100000 | 35023000
9 | 9 | 2026-01-31 | MCEL TKL 20260131 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 16000 | 237000
10 | 10 | 2026-02-28 | MCEL TKL 20260228 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 9000 | 228000
11 | 11 | 2026-04-30 | MCEL TKL 20260430 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 9000 | 219000
12 | 12 | 2026-05-29 |  |  | SC-004 | MS Engineering HK Limited | 文生工程有限公司 | 中土Project | 2500000 | 500000 | 1000000
13 | 13 | 2026-06-10 |  |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 06 | 40580000 | 1500000 | 33523000
14 | 14 | 2026-05-30 | MCEL TKL 20260131 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 9000 | 210000
15 | 15 | 2026-06-23 | DN3825015 |  | O-008 | Pneumoconiosis Compensation Fund Board | 肺塵埃沉着病補償基金委員會 | Levies | 350880 | 1635 | 349245
16 | 16 |  |  |  | O-009 | 0 | 0 | Miscellaneous | 2566 | 1900 | 666
17 | 17 | 2026-06-15 | INV-2026-037 |  | SC-004 | MS Engineering HK Limited | 文生工程有限公司 | 中土Project | 2500000 | 500000 | 500000
18 | 18 | 2026-07-06 | INV-2026-038 |  | SC-004 | MS Engineering HK Limited | 文生工程有限公司 | 中土Project | 2500000 | 500000 | 0
19 | 19 | 2026-07-07 | 10-2506-INV-007 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 07 | 40580000 | 1200000 | 32323000
20 | 20 | 2026-07-07 | 10-2506-INV-007V |  | O-007 | Wai Ho Engineering Limited | 煒浩工程有限公司 | CNP | 57420 | 11484 | 45936
21 | 21 | 2026-06-30 | MCEL TKL 20260131 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 9000 | 201000
22 | 22 | 2026-08-04 | DN3852969 |  | O-008 | Pneumoconiosis Compensation Fund Board | 肺塵埃沉着病補償基金委員會 | Levies | 350880 | 4987 | 344258
23 | 23 | 2026-08-08 | 10-2506-INV-008 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works IP - 08 | 40580000 | 1200000 | 31123000
24 | 24 | 2026-08-08 | 10-2506-INV-008V |  | O-007 | Wai Ho Engineering Limited | 煒浩工程有限公司 | CNP | 57420 | 5742 | 40194
25 | 25 | 2026-07-31 | MCEL TKL 20260731 ISA PTSO |  | O-003.1 | MCEL CONSULTANT LIMITED | 0 | Safety Audit | 42000 | 7000 | 35000
26 | 26 | 2026-08-11 | DN3544020 |  | O-006 | CONSTRUCTION INDUSTRY COUNCIL | 建造業議會 | 0.68% Levies | 350880 | 32145 | 318735
27 | 27 | 2026-08-31 | MCEL TKL 20260831 PTSO |  | O-003.2 | MCEL CONSULTANT LIMITED | 0 | RSO | 264000 | 9000 | 192000
28 | 28 | 2026-09-03 |  |  | O-009 | 0 | 0 | Miscellaneous | 2566 | 666 | 0
29 | 29 | 2026-10-12 | INV-2026-068 |  | SC-004.1 | MS Engineering HK Limited | 文生工程有限公司 | MS_Q2285 - 中國土木粉嶺 (N28) | 2000000 | 2000000 | 0
30 | 30 | 2026-10-08 | 10-2506-INV-009 |  | SC-001 | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works | 40580000 | 3000000 | 28123000
31 | 31 | 2026-10-06 | DN3894201 |  | O-008 | Pneumoconiosis Compensation Fund Board | 肺塵埃沉着病補償基金委員會 | Levies | 350880 | 2475 | 341783
32 | 32 | 2026-09-21 | DN2609002044 |  | O-011 | UCMG | 聯康醫療 | Body check | 5000 | 500 | 4500
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43
44 | 44
45 | 45
46 | 46
47 | 47
48 | 48
49 | 49
50 | 50
51 | 51
52 | 52
53 | 53
54 | 54
55 | 55
56 | 56
57 | 57
58 | 58
59 | 59
60 | 60
61 | 61
62 | 62
63 | 63
64 | 64
65 | 65
66 | 66
67 | 67
68 | 68
69 | 69
70 | 70
71 | 71
72 | 72
73 | 73
74 | 74
75 | 75
76 | 76
77 | 77
78 | 78
79 | 79
80 | 80
81 | 81
82 | 82
83 | 83
84 | 84
85 | 85
86 | 86
87 | 87
88 | 88
89 | 89
90 | 90
91 | 91
92 | 92
93 | 93
94 | 94
95 | 95
96 | 96
97 | 97
98 | 98
99 | 99
100 | 100
101 | 101
102 | 102
103 | 103
104 | 104
105 | 105
106 | 106
107 | 107
108 | 108
109 | 109
110 | 110
111 | 111
112 | 112
113 | 113
114 | 114
115 | 115
116 | 116
117 | 117
118 | 118
119 | 119
120 | 120
121 | 121
122 | 122
123 | 123
124 | 124
125 | 125
126 | 126
127 | 127
128 | 128
129 | 129
130 | 130
131 | 131
132 | 132
133 | 133
134 | 134
135 | 135
136 | 136
137 | 137
138 | 138
139 | 139
140 | 140
141 | 141
142 | 142
143 | 143
[9 empty] | 381153511.6 | 17612553.6
|  | Sub-IP No. | [7 empty] | MC IP-No. |  | Mepork (MC)
|  | 1 | 0 | 0 | [5 empty] | 1 |  | 0
|  | 2 | 0 | 0 | [5 empty] | 2 |  | 0
|  | 3 | 0 | 0 | [5 empty] | 3 |  | 0
|  | 4 | 0 | 0 | [5 empty] | 4 |  | 0
|  | 5 | 0 | 0 | [5 empty] | 5 |  | 0
|  | 6 | 0 | 0 | [5 empty] | 6 |  | 0
|  | 7 | 0 | 0 | [5 empty] | 7 |  | 0
|  | 8 | 0 | 0 | [5 empty] | 8 |  | 0
|  | 9 | 0 | 0 | [5 empty] | 9 |  | 0
|  | 10 | 0 | 0 | [5 empty] | 10 |  | 0 | Total Amount | TBC
|  |  | 0 | 0 | [7 empty] | 0 | 0 | 0

## Project Summary
美博工程服務有限公司
MS_Q1161_25_jc (MTR - K2297.C-25C Replacement of Platform Awnings at EAL Stations (Stage 3)
總承建商(MC): | Mepork Engineering Services Limited | [6 empty] | 承建金額: | 51600000
[8 empty] | (a) |  |  |  | $1,720,000.00 Contingency
[8 empty] | (A) Sub-total: | 51600000
Item | Sub-contractors' No. | Quotation Copy | Sub-contractors' Name | Company Name (in Chinese) | Nature of S/C Works | Contract Charge | Contract Sum | VO | Revised Contract Sum | Remark | 合約會簽表 (10萬以上) | Contract | 定標會議紀錄 (100萬以上) | 報價已簽名 | 正本已存檔 | OA
1 | SC-001 |  | Wai Ho Engineering Limited | 煒浩工程有限公司 | Whole works |  | 40580000 |  | 40580000
2 | O-002 |  | Storfield Insurance Consultants Ltd | 多福保險顧問有限公司 | Insurance |  | 515019.6 |  | 515019.6 | [6 empty] | 2025-12-12
3 | O-003.1 |  | MCEL CONSULTANT LIMITED |  | Safety Audit |  | 42000 |  | 42000 | $7,000/time; say 6 time | [5 empty] | 2026-02-27
4 | O-003.2 |  | MCEL CONSULTANT LIMITED |  | RSO |  | 264000 |  | 264000 | RSO $11,000/month | [5 empty] | 2026-02-27
5 | SC-004 |  | MS Engineering HK Limited | 文生工程有限公司 | 中土Project |  | 2500000 |  | 2500000 | [6 empty] | 2026-03-17
5.1 | SC-004.1 |  | MS Engineering HK Limited | 文生工程有限公司 | MS_Q2285 - 中國土木粉嶺 (N28) |  | 2000000 |  | 2000000 | [6 empty] | 2026-09-29
5A | O-005 |  |  |  | Others |  | 13200 |  | 13200 | from 財務數據
6 | O-006 |  | CONSTRUCTION INDUSTRY COUNCIL | 建造業議會 | 0.68% Levies |  | 350880 |  | 350880
7 | O-007 |  | Wai Ho Engineering Limited | 煒浩工程有限公司 | CNP |  | 57420 |  | 57420 | $2,871/次 (預計20次) | [5 empty] | 2026-06-30
8 | O-008 |  | Pneumoconiosis Compensation Fund Board | 肺塵埃沉着病補償基金委員會 | Levies |  | 350880 |  | 350880 | Say 0.68%
9 | O-009 |  |  |  | Miscellaneous |  | 2566 |  | 2566
10 | SC-010 | [7 empty] | 0
11 | O-011 |  | UCMG | 聯康醫療 | Body check |  | 5000 |  | 5000 | [6 empty] | 2026-10-06
12 | [8 empty] | 0
13 | [8 empty] | 0
14 | [8 empty] | 0
15 | [8 empty] | 0
16 | [8 empty] | 0
17 | [8 empty] | 0
18 | [8 empty] | 0
19 | [8 empty] | 0
20 | [8 empty] | 0
21 | [8 empty] | 0
22 | [8 empty] | 0
23 | [8 empty] | 0
[8 empty] | (B) Sub-total : | 46680965.6
| M-0XX | Material | [5 empty] | (C)Excluded Contract Charge item : | 0 | *
| SC-0XX | Sub-Contractor | [5 empty] | (C1) 財務會作調撥(人工分攤) | 800000 | 預800,000 for 人工分攤
| O-0XX | Other | [5 empty] | (D) = (B)+(C)+(C1): | 47480965.6
[8 empty] | (E) = (A)-(D)預計利潤: | 4119034.4
[8 empty] | 預計利潤率: | 7.983% | (原預計利潤率7%)